## Calendar
Date | Day | Phase | Platform(s) | Content type | Content idea / hook | Caption angle & CTA | Status
2026-08-24 | Mon | Phase 1 - Foundation | All | Setup | Create/clean up profiles (TikTok, IG, YouTube, X, LinkedIn, FB Page); same icon + bio + landing-page link everywhere | n/a - setup task | Not started
2026-08-24 | Mon | Phase 1 - Foundation | Product Hunt | Setup | Claim maker profile + “coming soon” page (start now - needs the longest lead time) | n/a - setup task | Not started
2026-08-25 | Tue | Phase 1 - Foundation | Reddit | Community | Start genuinely participating in target subs (r/TestFlight, r/iOSBeta, r/IndieDev, r/SideProject, r/iosgaming) - comment, don't post yet | n/a - reputation building | Not started
2026-08-25 | Tue | Phase 1 - Foundation | TikTok + IG Reels + YT Shorts | Video | Satisfying reveal #1: scramble-to-solve time-lapse of a random photo, trending audio, no talking | Free beta - keep it forever. Link in bio. | Not started
2026-08-26 | Wed | Phase 1 - Foundation | X | Post | Announcement: preorders are open on the App Store | apps.apple.com/app/id6776386637 - #buildinpublic #indiedev | Not started
2026-08-26 | Wed | Phase 1 - Foundation | LinkedIn | Post | Founder post: launching a solo-built iOS puzzle game, preorders open | apps.apple.com/app/id6776386637 | Not started
2026-08-27 | Thu | Phase 1 - Foundation | TikTok + IG Reels + YT Shorts | Video | Mode spotlight 1/7: Slide | Free beta - link in bio, keep it forever | Not started
2026-08-28 | Fri | Phase 1 - Foundation | Facebook | Setup + post | Create Page, cross-post satisfying reveal clip; identify 2-3 relevant Groups to join | n/a - setup task | Not started
2026-08-29 | Sat | Phase 1 - Foundation | TikTok + IG Reels + YT Shorts | Video | Free-forever hook: text-over-video - join the beta now, keep the full app free forever | testflight.apple.com/join/7FvEWNPR | Not started
2026-08-30 | Sun | Phase 1 - Foundation | X | Post | Build-in-public: a SwiftUI/design decision behind one of the 7 modes | #SwiftUI #indiedev #iosdev | Not started
2026-08-31 | Mon | Phase 2 - Beta push | Reddit | Post | r/TestFlight - seeking beta testers post | testflight.apple.com/join/7FvEWNPR | Not started
2026-09-01 | Tue | Phase 2 - Beta push | TikTok + IG Reels + YT Shorts | Video | Mode spotlight 2/7: Swap | Free beta - link in bio | Not started
2026-09-02 | Wed | Phase 2 - Beta push | X | Post | Poll: which mode looks the most fun? (with clip) | #indiedev | Not started
2026-09-03 | Thu | Phase 2 - Beta push | Reddit | Post | r/iOSBeta - beta invite post (check thread format/rules first) | testflight.apple.com/join/7FvEWNPR | Not started
2026-09-03 | Thu | Phase 2 - Beta push | TikTok + IG Reels + YT Shorts | Video | Satisfying reveal #2: different photo genre (e.g. a pet photo) | Free beta - link in bio, keep it forever | Not started
2026-09-05 | Sat | Phase 2 - Beta push | TikTok + IG Reels + YT Shorts | Video | Behind-the-scenes: solo-dev workspace / Xcode timelapse building a feature | Building this solo with SwiftUI - beta's open, link in bio | Not started
2026-09-06 | Sun | Phase 2 - Beta push | LinkedIn | Post | Founder update: beta is open, what I've learned so far | testflight.apple.com/join/7FvEWNPR | Not started
2026-09-07 | Mon | Phase 2 - Beta push | Facebook | Group post | Share a clip in 1-2 relevant Groups (mobile puzzle-game fans, iOS app communities) - follow each group's rules | testflight.apple.com/join/7FvEWNPR | Not started
2026-09-08 | Tue | Phase 2 - Beta push | TikTok + IG Reels + YT Shorts | Video | Mode spotlight 3/7: Time Trial + Gauntlet Ladder | Free beta - link in bio | Not started
2026-09-09 | Wed | Phase 2 - Beta push | X | Post | Dev-log: a bug/challenge solved this week | #buildinpublic #iosdev | Not started
2026-09-10 | Thu | Phase 2 - Beta push | TikTok + IG Reels + YT Shorts | Video | Daily Challenge feature: one seeded puzzle a day + streak calendar | Free beta - link in bio, keep it forever | Not started
2026-09-11 | Fri | Phase 2 - Beta push | Reddit | Post | r/IndieDev or r/SideProject - “I built a sliding-puzzle app solo with SwiftUI” story post | testflight.apple.com/join/7FvEWNPR | Not started
2026-09-12 | Sat | Phase 2 - Beta push | TikTok + IG Reels + YT Shorts | Video | Chaos mode reveal: source image recolored/mirrored/flipped before you see it | Free beta - link in bio | Not started
2026-09-13 | Sun | Phase 2 - Beta push | LinkedIn | Post | Milestone: beta-tester count / early feedback highlights | testflight.apple.com/join/7FvEWNPR | Not started
2026-09-14 | Mon | Phase 3 - Spotlights & outreach | X | Post | Beta-tester quote/reaction shoutout | #indiedev | Not started
2026-09-15 | Tue | Phase 3 - Spotlights & outreach | TikTok + IG Reels + YT Shorts | Video | Mode spotlight 4/7: Haze (fog reveal, shake to peek) | Free beta - link in bio, keep it forever | Not started
2026-09-16 | Wed | Phase 3 - Spotlights & outreach | Outreach | Email/DM | Send personal notes to a handful of iOS newsletters + small YouTubers/TikTokers covering indie apps/puzzle games, with TestFlight link + best clips | testflight.apple.com/join/7FvEWNPR | Not started
2026-09-17 | Thu | Phase 3 - Spotlights & outreach | TikTok + IG Reels + YT Shorts | Video | Achievements & Wall of Fame showcase (39 achievements, pinned record cards) | Free beta - link in bio | Not started
2026-09-18 | Fri | Phase 3 - Spotlights & outreach | Reddit | Post | r/iosgaming - gameplay clip + a couple of beta-tester reactions | testflight.apple.com/join/7FvEWNPR | Not started
2026-09-19 | Sat | Phase 3 - Spotlights & outreach | TikTok + IG Reels + YT Shorts | Video | Widgets + Live Activity demo (Lock Screen / Dynamic Island) | Free beta - link in bio, keep it forever | Not started
2026-09-20 | Sun | Phase 3 - Spotlights & outreach | LinkedIn | Post | Founder post: finishing touches before launch, what's shipped so far | apps.apple.com/app/id6776386637 | Not started
2026-09-20 | Sun | Phase 3 - Spotlights & outreach | Product Hunt | Prep | Finalize gallery images, tagline, and draft the maker's first comment | n/a - prep task | Not started
2026-09-21 | Mon | Phase 4 - Countdown | X | Post | Countdown: 7 days to launch | testflight.apple.com/join/7FvEWNPR (last week for the free-forever hook) | Not started
2026-09-22 | Tue | Phase 4 - Countdown | TikTok + IG Reels + YT Shorts | Video | “9 days left” style countdown + preorder reminder | apps.apple.com/app/id6776386637 - preorder now | Not started
2026-09-23 | Wed | Phase 4 - Countdown | Facebook | Post + group | Countdown post to Page + relevant Groups | apps.apple.com/app/id6776386637 | Not started
2026-09-24 | Thu | Phase 4 - Countdown | TikTok + IG Reels + YT Shorts | Video | Speed-solve challenge: “beat my time” (duet/stitch bait) | Free beta closes at launch - link in bio | Not started
2026-09-24 | Thu | Phase 4 - Countdown | Product Hunt | Prep | Message the 10-15 people who'll check the listing in the first hour of launch day | n/a - do this today, not the night before | Not started
2026-09-25 | Fri | Phase 4 - Countdown | Reddit | Post | Final beta-tester call across active threads/subs before launch | testflight.apple.com/join/7FvEWNPR | Not started
2026-09-26 | Sat | Phase 4 - Countdown | TikTok + IG Reels + YT Shorts | Video | Beta-tester testimonial/highlight-reel compilation | Launching Monday - link in bio | Not started
2026-09-26 | Sat | Phase 4 - Countdown | LinkedIn | Post | “2 days to launch” founder post | apps.apple.com/app/id6776386637 | Not started
2026-09-27 | Sun | Phase 4 - Countdown | All | Post | Launch-eve hype post: “tomorrow it's live” | apps.apple.com/app/id6776386637 | Not started
2026-09-28 | Mon | Launch | Product Hunt | Launch | Submit listing at 8:00 AM UK time (12:01 AM PT reset); post maker's first comment immediately | Ask people to check it out & share feedback - never 'please upvote' | Not started
2026-09-28 | Mon | Launch | All bios/links | Update | Switch every bio/CTA link from TestFlight to the App Store | apps.apple.com/app/id6776386637 | Not started
2026-09-28 | Mon | Launch | TikTok + IG Reels + YT Shorts | Video | Launch day announcement - it's live | Download now - apps.apple.com/app/id6776386637 | Not started
2026-09-28 | Mon | Launch | X | Post | Launch post + live-tweet Product Hunt progress through the day | Link to PH listing + App Store | Not started
2026-09-28 | Mon | Launch | Reddit | Post | Launch announcement where community rules allow (avoid duplicate text across subs) | apps.apple.com/app/id6776386637 | Not started
2026-09-28 | Mon | Launch | LinkedIn + Facebook | Post | Launch announcement, native wording per platform | apps.apple.com/app/id6776386637 | Not started
2026-09-28 | Mon | Launch | All | Engagement | Reply to every comment on PH, Reddit, and social posts throughout the day | n/a - full-day priority | Not started
2026-09-29 | Tue | Post-launch | All | Post | Thank-you post to beta testers and early supporters (tag with permission) | n/a | Not started
2026-09-30 | Wed | Post-launch | X + LinkedIn | Post | Product Hunt results recap - final ranking, what happened | n/a | Not started
2026-10-01 | Thu | Post-launch | TikTok + IG Reels + YT Shorts | Video | Post-launch highlight reel / thank you | Leave a review if you're enjoying it! apps.apple.com/app/id6776386637 | Not started
2026-10-01 | Thu | Post-launch | All | Ask | Direct review ask to players who've been active a few days (once, not repeatedly) | n/a | Not started
2026-10-04 | Sun | Post-launch | X + LinkedIn | Post | Build-in-public recap: “we launched, here's what happened” | n/a | Not started

## Summary
9 Tiles Puzzle - Campaign Summary
Mon Aug 24 - Mon Sep 28, 2026 (5 weeks) + post-launch week
By status
Not started | 53
Scheduled | 0
Posted | 0
Skipped | 0
Total items | 53
By phase
Phase 1 - Foundation | 10
Phase 2 - Beta push | 14
Phase 3 - Spotlights & outreach | 8
Phase 4 - Countdown | 9
Launch | 7
Post-launch | 5
By platform (contains-match; a row may count toward multiple)
TikTok | 17
IG Reels | 17
YT Shorts | 17
X | 9
Reddit | 7
LinkedIn | 8
Facebook | 4
Product Hunt | 4

## Video Shot Lists
Date | Video Title | Length | What to record (shot list) | On-screen text & timing | Music vibe | Editing notes | Caption (copy-paste)
2026-08-25 | Satisfying Reveal #1 | 10-15s | Pick a vivid, high-contrast photo ahead of time (via the Photos-library source, not a random fetch, so it reads well small). Screen-record: 1s on the intact photo, the shuffle into a 4x4/5x5 grid, then a smooth practiced solve. Take 2-3 tries, keep the cleanest. | None for first 8s - let the visual carry it. Last 2s: 'Free beta - link in bio, keep it forever' in accent orange (#FF8A3D). | Upbeat trending 'satisfying' audio - check TikTok Trending Sounds the day you post. | Speed up the shuffle 2x. Real time (or a hair of slow-mo) on the final few moves of the solve so the 'aha' lands. Hard cut, hold 1s on the completed image before the CTA card. | Watch this come back together. Free beta open now - keep the full app forever if you test it. Link in bio. #satisfying #puzzle #iosgames #mobilegame #indiedev
2026-08-27 | Mode Spotlight: Slide | 15-20s | Open Slide mode. Solve a few tiles normally, then deliberately nudge an already-placed tile to show the twist, finish the solve. | 0-1s title card 'SLIDE MODE'. Caption timed to the nudge: 'tiles you've placed... can still move'. | Clean, mid-energy beat - start of a consistent 'mode spotlight' music family. | Briefly slow down right as you nudge the placed tile so it reads clearly; real time otherwise. | Mode 1 of 7: Slide. Even the tiles you've already placed aren't totally safe. Free beta - link in bio. #iosgames #puzzlegame #indiedev
2026-08-29 | Free Forever Hook | 8-12s | Fast montage - reuse 2-3 clips from the first satisfying reveal as backdrop. No new gameplay needed. | Text-driven: 'Beta testers keep the FULL APP' -> 'FREE. FOREVER.' -> 'Link in bio'. Text is the star, gameplay is backdrop. | Upbeat, with text timed to hit on the beat. | Cut on the beat; keep each text card on screen ~1s. | The best time to try 9 Tiles Puzzle is before it launches. Beta testers keep the full app free, forever. Link in bio. #iosdev #indiedev #freeapp
2026-09-01 | Mode Spotlight: Swap | 15-20s | Open Swap mode. Show swapping two tiles, then a correct tile locking permanently the moment it lands right. | Title card 'SWAP MODE'. Caption: 'swap any two tiles' then 'get it right and it locks - for good'. | Same clean mid-energy family as Slide, for series consistency. | Quick zoom/flash the instant a tile locks in place. | Mode 2 of 7: Swap - land a tile correctly and it's locked in for good. Free beta, link in bio. #puzzlegame #iosgames
2026-09-03 | Satisfying Reveal #2 | 10-15s | Same format as Reveal #1, different photo genre for variety (e.g. a pet or food photo - different color palette). | Same as Reveal #1. | A different trending track than Reveal #1 - don't repeat audio back to back. | Repeat the proven structure from Reveal #1 exactly. | Round two. Free beta - link in bio, keep it forever. #satisfying #puzzle #mobilegame #indiedev
2026-09-05 | Behind the Scenes: Building It | 15-25s | Screen-record a short Xcode session - real SwiftUI code, running the simulator. Optional: a couple seconds of you on camera if comfortable. | 'Building this solo.' then one concrete detail, e.g. 'Swift 6, SwiftUI, no third-party UI libraries.' | Calmer, lo-fi/coding-vibe track. | Speed-ramp the typing/scrolling 3-4x; real time on the simulator running the feature. | Solo dev diary: building 9 Tiles Puzzle in SwiftUI. Beta's open if you want to help test - link in bio. #buildinpublic #indiedev #SwiftUI #iosdev
2026-09-08 | Mode Spotlight: Time Trial | 15-20s | Show the countdown timer under pressure, then cut to the Gauntlet Ladder screen (the 10-stage climb). | 'TIME TRIAL' then 'Gauntlet Ladder: 10 stages'. | Higher-energy, tense track matching the time pressure. | Slight speed-up on the clock ticking to build tension; real time on the actual solve. | Mode 3 of 7: Time Trial. Beat the clock, then climb all 10 stages of the Gauntlet Ladder. Free beta, link in bio. #iosgames #puzzlegame
2026-09-10 | Daily Challenge | 15-20s | Open Daily Challenge, solve the day's puzzle, then show the calendar view with the streak marked. | 'One puzzle. Every day.' then 'track your streak'. | Warm, steady mid-tempo track. | Real time throughout; brief pause/zoom on the calendar streak. | One seeded puzzle a day, and a calendar to track (or replay) your streak. Free beta, link in bio. #dailychallenge #iosgames #puzzlegame
2026-09-12 | Chaos Mode Reveal | 10-15s | Start the mode, capture the moment the photo turns out recolored/mirrored/flipped from what you expected, then the solve. | Minimal - just a 'CHAOS MODE' title card, then nothing until the CTA. Let the twist speak for itself. | A track with a hard 'drop' timed to the recolor/mirror reveal. | Hard cut or glitch-style transition right at the reveal for maximum surprise. | Mode 7 of 7: Chaos. You don't even know what the photo looks like until it's too late. Free beta, link in bio. #puzzlegame #iosgames #satisfying
2026-09-15 | Mode Spotlight: Haze | 15-20s | Show tiles obscured by drifting fog, physically shake the phone on camera to reveal briefly, keep solving mostly blind. | 'HAZE MODE' then 'shake to peek'. | Moody/ambient into a beat drop right as you shake. | Quick zoom/flash on the shake moment. | Mode 4 of 7: Haze. The tiles hide behind fog - shake your phone to peek. Free beta, link in bio. #iosgames #puzzlegame
2026-09-17 | Achievements & Wall of Fame | 15-25s | Capture an achievement unlocking (toast/animation), then pan the Wall of Fame cork board of pinned record cards - flick one to show its swing physics. | '39 achievements' then 'Wall of Fame - your best records, pinned'. | Celebratory, rewarding track. | Slow-mo on the achievement unlock animation; real time flicking a Wall of Fame card. | 39 achievements to unlock, plus a Wall of Fame for your best records - physics and all. Free beta, link in bio. #iosgames #achievements
2026-09-19 | Widgets + Live Activity | 15-20s | Record from the Lock Screen showing the Live Activity / Dynamic Island tracking an in-progress puzzle, then swipe home and show the 3 widgets (Daily Challenge, Streaks & Records, Resume Game). | 'Track your puzzle from the Lock Screen' then '3 home screen widgets'. | Clean, modern tech-demo style track. | Real time; end on tapping a widget to deep-link back into the game. | Your puzzle, tracked from the Lock Screen and Dynamic Island - plus 3 home screen widgets. Free beta, link in bio. #iosgames #widgets #iOS26
2026-09-22 | Countdown / Preorder Reminder | 8-12s | Quick highlight montage reusing your best clips so far - no new filming required. | '9 days.' then '9 Tiles Puzzle' then 'Preorder now - link in bio'. | Building, anticipatory track. | Cut on the beat; text-forward, gameplay as backdrop. | 9 days until launch. Preorder now, link in bio. #iosgames #launchday #indiedev
2026-09-24 | Speed-Solve Challenge | 10-15s | Record a genuinely fast, clean solve with the in-game timer visible on screen. | 'My time: [X.XX]s' then 'beat it?' as a duet/stitch prompt. | High-energy track suited to a challenge format. | Keep it real-time so the time is legitimate; optional slow-mo replay of just the final move. | My best time - think you can beat it? Duet this with your run. Free beta, link in bio. #speedrun #puzzlegame #challenge
2026-09-26 | Beta Tester Highlight Reel | 20-30s | Compile 3-5 short clips or quotes from real beta testers (get their OK first) - their gameplay, or text-over-video of what they told you. | Each tester's quote as its own caption card; first names only unless they're happy to be tagged. | Warm, community-feel track. | Quick cuts between testers, ~3-5s each. | What beta testers are saying. Launching Monday - link in bio. #buildinpublic #indiedev #betatest
2026-09-28 | Launch Day Announcement | 10-15s | Re-cut your best existing solve clip, or freshly record downloading/opening the app live from the App Store. | 'IT'S LIVE' then 'Download now - link in bio'. | Celebratory, high-energy trending track. | Fast cuts; confetti/celebration-style text animation if your editor has one. | 9 Tiles Puzzle is live on the App Store. Download now, link in bio. #launchday #iosgames #newapp
2026-10-01 | Post-Launch Thank You | 15-20s | A calmer, more personal clip - optionally you on camera, or text over a montage of the campaign's best moments. | 'Thank you.' then 'If you're enjoying it, a review means everything' then the App Store link. | Warm, low-key track. | Slower pacing than launch day; montage of highlights from the whole campaign. | Thank you to everyone who tested, shared, and downloaded. If you're enjoying 9 Tiles Puzzle, a review would mean a lot. Link in bio. #indiedev #iosgames #thankyou